## Portfolio
Capex Book Id | Project Number | Department | Project Name | Flag | Stage | Owner Type | Project Manager C&I | State | City | Region | Program | Design Build Company Name | Project Total Value | Ytd Actuals Paws | Spend To Date (Includes Prior Years) | 1. Design Start Date | 2. Permit Submission Date | 3. Construction Start Date | Temp Fbo Substantial Completion Date | Charter Terminal Substantial Completion | Gse Substantial Completion Date | Demo #1 Substantial Completion Date | Demo #2 Substantial Completion Date | Demo #3 Substantial Completion Date | Demo #4 Substantial Completion Date | Reno # 1 Substantial Completion Date | Reno # 2 Substantial Completion Date | Ramp # 1 Substantial Completion Date | Ramp # 2 Substantial Completion Date | Ramp # 3 Substantial Completion Date | Ramp # 4 Substantial Completion Date | Ramp # 5 Substantial Compeltion Date | Ramp # 6 Substantial Completion Date | Ramp # 7 Substantial Completion Date | Hangar # 1 Substantial Completion Date | Hangar # 2 Substantial Completion Date | Hangar # 3 Substantial Completion Date | Office # 1 Substantial Completion Date | Office # 2 Substantial Completion Date | Office # 3 Substantial Completion Date | Fbo #1 Substantial Completion Date | Fbo #2 Substantial Completion Date | Fbo #3 Substantial Completion Date | Ff & E # 1 Completion Date | Ff & E # 2 Completion Date | Ff & E # 3 Completion Date | Opening Date Hangar # 1 | Opening Date Hangar # 2 | Opening Date Temp Fbo | Opening Date Fbo | # Hangars | # Fbo Terminal | # Gse | # Ramps | # Parking Lot | # Offices | Fbo Terminal Sq Ft | Hangar Sq Ft | Office Space Sq Ft | Parking Lot Sq Ft | Ramp Sq Ft | Renovation Sq Ft (Other) | Gse Sq Ft | Fbo Terminal (Emea) | Fbo Terminal Sq Mt | Fuel Farm (Emea) | Fuel Farm Sq Ft | Hangar (Emea) | Hangar Sq Mt | Refit (Emea) | Refit Sq Mt | Remodel (Emea) | Remodel Sq Mt
8 | 123-45-678 | Construction and Infrastructure | ABC | Yellow | 3. Construction | Name Last Name | Name Last Name - Name and Last Name | Florida | Jacksonville | South | United States | Company Name | 16.1 |  |  | 2024-05-01 | 2026-05-19 | 2025-09-02 | [9 empty] | 2026-06-30 | [6 empty] | 2026-07-01 | [11 empty] | 2026-08-20 |  |  |  | 1 |  |  | 1 |  | 1 |  | 39701 | 2500 |  | 57000
124 | 308-35-876 | Construction and Infrastructure 2 | ABC-1 | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Hawaii | Lihue | West | Hawaii Program | Company Name | 7.9 |  |  | 2024-12-16 | 2026-06-08 | 2026-09-14 |  |  | 2026-10-09 | [19 empty] | 2027-03-03 |  |  | 2027-04-03 | [5 empty] | 2027-04-03 |  | 1 | 1 | 1 |  |  | 1400 |  |  |  | 50000 |  | 3000
125 | 254-87-356 | Construction and Infrastructure | ABC 1 | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Hawaii | Kahului, | West | Hawaii Program | Company Name | 8.3 |  |  | 2024-12-16 | 2026-03-31 | 2026-08-19 | [7 empty] | 2026-06-23 | [14 empty] | 2027-12-27 |  |  | 2028-01-27 | [5 empty] | 2028-01-27 |  | 1 | 1 |  |  |  | 4000 | [5 empty] | 3000
126 | 123-45-678 | Construction and Infrastructure 2 | ABC I | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Hawaii | Kailua Kona | West | Hawaii Program | Company Name | 14.6 |  |  | 2024-12-16 | 2026-05-01 | 2026-04-29 |  |  | 2026-08-18 | [6 empty] | 2028-01-14 | [12 empty] | 2027-06-25 |  |  | 2027-07-25 | [5 empty] | 2025-07-25 |  | 1 | 1 | 1 | 1 |  | 3000 |  |  | 45796 | 550000 |  | 3000
127 | 308-35-876 | Construction and Infrastructure | ABC | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Hawaii | Hilo | West | Hawaii Program | Company Name | 3.6 | 6 | 8 | 2024-12-16 | 2026-06-10 | 2026-08-19 | [22 empty] | 2027-09-08 |  |  | 2027-10-08 | [5 empty] | 2027-10-08 |  | 1 |  |  |  |  | 1200 | [5 empty] | 3725
131 | 254-87-356 | Construction and Infrastructure | ABC-1 | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Hawaii | Honolulu | West | Hawaii Program | Company Name | 6.9 |  |  | 2024-12-16 | 2026-01-26 | 2026-07-15 | [7 empty] | 2026-04-30 | [14 empty] | 2027-10-22 |  |  | 2027-11-15 | [5 empty] | 2027-11-15 |  | 1 |  |  |  |  | 5000 |  |  |  |  | 21582
5 | 123-45-678 | Construction and Infrastructure | ABC 1 | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | New Hampshire | Manchester | East | United States | Company Name | 11.8 |  |  | 2026-06-27 | 2025-10-01 | 2027-01-04 | [16 empty] | 2027-10-31 | [11 empty] | 2027-12-31 | [10 empty] | 29471 | 3181
15 | 308-35-876 | Construction and Infrastructure | ABC I | Red | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Connecticut | Windsor Locks | East | United States | Company Name | 19.8 |  |  | 2026-05-01 | 2026-05-01 | 2026-12-04 | [9 empty] | 2028-06-04 | [6 empty] | 2028-06-04 | [22 empty] | 40000 | 6530 | 12000 | 63450
12 | 254-87-356 | Construction and Infrastructure | Project Name | Yellow | 3. Construction | Name Last Name | Name Last Name - Name and Last Name | Florida | Tampa | South | United States | Company Name | 13.5 |  |  | 2022-04-01 | 2024-04-01 | 2025-06-30 | [9 empty] | 2026-07-31 | [6 empty] | 2026-07-31 | [22 empty] | 30000 | 3300
30 | 123-45-678 | Construction and Infrastructure | Project Name | Green | 3. Construction | Name Last Name | Name Last Name - Name and Last Name | Massachusetts | Bedford | East | United States | Company Name | 20.8 |  |  | 2025-10-02 | 2026-02-02 | 2026-04-27 | [8 empty] | 2026-12-31 | [8 empty] | 2026-07-15 | 2026-12-31 | [13 empty] | 2 | [6 empty] | 40798 | 60076
64 | 308-35-876 | Construction and Infrastructure 2 | Project Name | Red | 4. Close Out | Name Last Name | Name Last Name - Name and Last Name | Virginia | Norfolk | East | United States | Company Name | 30.7 |  |  | 2025-11-10 | 2026-03-20 | 2026-10-13 | [9 empty] | 2027-11-08 | [6 empty] | 2027-12-08 | 2027-12-08 | [10 empty] | 2028-02-10 | 2028-02-10 |  |  | 2 |  |  | 1 | 1 |  |  | 60000 | 8750 | 38600 | 167000
66 | 254-87-356 | Construction and Infrastructure | Project Name | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Virginia | Roanoke | East | United States | Company Name | 14 | 5 | 8 | 2025-06-09 | 2026-05-21 | 2026-05-26 | [16 empty] | 2028-03-06 | [22 empty] | 22000 | 300
68 | 123-45-678 | Construction and Infrastructure | Project Name | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Florida | Fort Myers | South | United States | Company Name | 31.2 |  |  | 2025-08-01 | 2026-06-03 | 2027-01-05 | [9 empty] | 2028-03-06 | [12 empty] | 2028-03-06 | [5 empty] | 2028-03-06 | [9 empty] | 4600 | 24000 | 3000 |  | 250000
70 | 308-35-876 | Construction and Infrastructure | Project Name | Green | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | California | San Francisco | West | United States | Company Name | 52.7 |  |  | 2025-11-03 | 2026-10-26 | 2026-10-12 |  | 2028-12-18 | 2027-05-31 | [13 empty] | 2027-05-31 | [5 empty] | 2027-03-26 | 2028-11-14 |  | 2028-12-15 | [5 empty] | 2028-12-15 | 1 | 2 | 1 |  | 1 |  | 22800 | 6000 |  | 25000 |  |  | 3000
120 | 254-87-356 | Construction and Infrastructure 2 | Project Name |  | 0. Waiting for Assignment | Name Last Name | Name Last Name - Name and Last Name | Virginia | Charlottesville | East | United States | Company Name | 3.6 | [47 empty] | 156000
128 | 123-45-678 | Construction and Infrastructure | Project Name | Green | 3. Construction | Name Last Name | Name Last Name - Name and Last Name | New Jersey | Teterboro | East | United States | Company Name | 2.1 | 2.8 | 2.9 | 2024-09-05 | 2025-11-24 | 2025-12-22 |  |  |  | 2026-04-03 |  |  |  | 2026-12-30 |  | 2026-04-15 | [12 empty] | 2026-12-30 | [12 empty] | 1 | [6 empty] | 47075
142 | 308-35-876 | Construction and Infrastructure | Project Name | Yellow | 2. Planning and Design | Name Last Name | Name Last Name - Name and Last Name | Virginia | Dulles | East | United States | Company Name | 22 |  |  | 2025-10-23 | 2025-12-23 | 2026-08-10 |  |  | 2026-12-28 |  |  |  |  | 2027-03-26 |  | 2026-10-23 | 2027-03-19 | 2027-04-23 |  | 2027-03-27 | [28 empty] | 467220 |  | 4500
41 | 254-87-356 | Construction and Infrastructure | Project Name |  | 1. Ideation | Name Last Name | Name Last Name - Name and Last Name | Massachusetts | Boston | East | United States | Company Name | 58.8 | [47 empty] | 40000
27 | 123-45-678 | Construction and Infrastructure | PRO - Ph 1 | Green | 0. Waiting for Assignment | Name Last Name | Name Last Name - Name and Last Name | Georgia | Savannah, | South | United States | Company Name | 36 |  |  | 2024-01-01 | [40 empty] | 7000 | 39900 | 3000 | 10000
40 | 308-35-876 | Construction and Infrastructure | PRO - Ph 1 | Green | 3. Construction | Name Last Name | Name Last Name | France | Paris | EMEA | EMEA | Company Name | 31.2 |  |  | 2024-05-17 |  | 2025-03-31 | [9 empty] | 2025-11-26 | [6 empty] | 2027-01-29 | [5 empty] | 2026-07-30 | [9 empty] | 3 | 1 |  | 1
43 | 254-87-356 | Construction and Infrastructure | PRO - Ph 1 | Green | 3. Construction | Name Last Name | Name Last Name | France | Paris | EMEA | EMEA | Company Name | 22 | 3 | 1 | [35 empty] | 1 | [14 empty] | New Build | 5000
53 | 123-45-678 | Construction and Infrastructure 2 | PRO - Ph 1 | Green | 3. Construction | Name Last Name | Name Last Name | Italy | Milan | EMEA | EMEA | Company Name | 58.8 | 5 | 4 | [12 empty] | 2025-08-22 | [6 empty] | 2026-10-13 | 2026-10-13 |  |  |  |  | 2026-10-13 |  |  | 2026-10-22 | [5 empty] | 2026-10-30 | [13 empty] | New Build | 433 |  |  |  | 0 |  | 0
93 | 308-35-876 | Construction and Infrastructure | PRO - Ph 1 | Green | 3. Construction | Name Last Name | Name Last Name | Italy | Milan | EMEA | EMEA | Company Name | 36 | 8 | 0 | [54 empty] | Renovation | 150
100 | 254-87-356 | Construction and Infrastructure | PRO - Ph 1 | Green | 3. Construction | Name Last Name | Name Last Name | London | London | EMEA | EMEA | Company Name | 31.2 | 6 | 2 | [10 empty] | 2026-12-31 | [44 empty] | 153
[35 empty] | 2028-05-25 | [5 empty] | 2028-03-24
[35 empty] | 2028-02-03 | 2028-03-28 | [10 empty] | 2028-03-28 | 2028-03-28 |  |  | 2 |  |  | 1 | 1
[35 empty] | 2027-04-19 | 2027-06-09 | [14 empty] | 2
[28 empty] | 2027-12-03 | [6 empty] | 2028-12-13 | 2028-12-13 | [12 empty] | 2026-12-11 |  | 2 | 1 | 2 | 1 | 1 | 2
2027-04-05
2026-05-06
[35 empty] | 2026-10-30 | 2026-10-30
2026-09-01
[38 empty] | 2026-06-03 | [12 empty] | 1
[28 empty] | 2027-01-18 | [12 empty] | 2027-08-05 | [8 empty] | 2027-09-02 |  | 1 |  | 1 | 1
[26 empty] | 2026-06-05 | [8 empty] | 2027-08-11 | [5 empty] | 2026-08-24 | 2027-11-01 |  |  |  |  | 2026-08-04
[41 empty] | 2026-01-15 | [10 empty] | 1
[38 empty] | 2026-08-31 | 2026-10-30 |  |  |  |  | 2026-06-29 | 2026-08-24 | 2026-10-26 |  |  |  | 2026-08-03
2027-07-26
[28 empty] | 2027-01-15 | 2027-06-18 | [8 empty] | 2028-08-25 | 2029-03-23 |  | 2029-06-29 |  |  | 2026-11-20 | [5 empty] | 2029-07-29 |  | 2 |  | 2 | 1 | 2
[28 empty] | 2026-02-26 | [6 empty] | 2026-02-26 |  |  | 2026-02-26 | [12 empty] | 1 |  |  | 1 |  | 1
[41 empty] | 2026-12-10 |  |  | 2026-12-30 | [7 empty] | 1 |  |  | 1
[41 empty] | 2024-06-15 | [5 empty] | 2026-05-11 | 2026-06-19
[26 empty] | 2026-12-01 | 2027-11-19 | [7 empty] | 2027-11-23 | [5 empty] | 2028-03-22 | 2028-03-22 |  |  |  |  | 2027-12-27 |  |  |  | 1 |  |  |  |  | 1
[26 empty] | 2027-12-31 | [8 empty] | 2027-08-05 | [8 empty] | 2027-08-05 | 2027-12-31 | [5 empty] | 1 |  |  |  |  | 1
[51 empty] | 1 | 1
0
10.5
5.5
[13 empty] | 1.74 |  |  | 2026-05-01